Budget Narrative HST-AR-18141

Section I:	Technical Program Summary (1 page maximum)

Outer Solar System Binaries (OSSBs) encode information about a variety of planet formation processes. HST has invested a significant amount of solar system observations to discover these binaries which this proposal will leverage to estimate the true underlying properties of OSSBs. This involves combining which binary companions were detected (from previous work) with determining which companions could have been detected if they were actually present. These detection limits provide the constraints for the to-be-developed BINary Orbit Population Simulator (BINOPS) to test different binary population models (e.g., the true frequency of OSSBs as a function of binary orbit size and solar system population). Note that the scope of the proposed work is significantly lower than the original Phase I proposal due to receiving ~22% of the proposed funding.

In this Archival program, we have three main Science Goals:

- Estimate the Detection Probability of binary companions as a function of separation and brightness for OSSBs. We will use PSF fitting on typical objects to identify heuristic function approximations broadly applicable to nearly all 500+ OSSBs.

- Develop the BINOPS model: a forward model that takes basic population parameters (e.g., frequency as a function of binary separation, eccentricity, inclination and the dynamical classification of the small body) and generates a synthetic true “physical” population, an observational bias model that turns this population into a synthetic “observed” population using previously calculated Detection Probabilities, and a Bayesian likelihood calculator that determines the probability of a match between the synthetic observed population and the actual HST observed population.

- Use Bayesian parameter inference on BINOPS to determine the properties of the actual true physical population of OSSBs. This will leverage extensive CPU resources of the BYU supercomputer. Either through these results or through specific model fits, we will address:

  - Whether the frequency of binaries around Jupiter Trojans, Centaurs, Cold TNOs, and Hot TNOs could be the same, even though it appears observationally that Trojans and Centuars have far fewer binaries (~3%) compared to TNOs (~30%).

  - Whether the frequency of binaries is consistent around Cold TNOs and Hot TNOs of the same size / absolute magnitude range (e.g,. 6 < H < 8).

  - In the Hot TNO population, at what size / absolute magnitude do binaries change properties from “moon”-like high-brightness-ratio close-in binaries around large TNOs to “binary”-like low-brightness-ratio wide binaries.

We propose to publish these results in at least one paper. Some goals may be approximated due to limited funding.

Section II:	Program Planning and Execution (5 page maximum)

Section required for Program Admin PIs only. Explain how the overall project will be carried out by all institutions. Provide a concise outline of the complete project and describe how it will be managed and executed across the entire program. Additionally, for each science goal stated in the Phase I proposal, complete the following subsection. Repeat this format for each science goal.

- Science Goal #1: (Insert short description of goal)

  - Describe the effort necessary for this science goal and all tasks to be performed.

  - Identify anticipated publications.

  - Include the sequence and timeline for the effort.

We begin this Section by summarizing the role of the different potential contributors to this project.

All the funding for this proposal is going to Admin PI / Science PI Darin Ragozzine at Brigham Young University and his students (including Co-I Dallin Spencer, a graduate student). Co-I Benjamin Proudfoot (University of Central Florida / Florida Space Institute) and Co-I Will Grundy (Lowell / Northern Arizona University) will not receive any funding. They may contribute by sharing code, as scientific consultants, or as co-authors at their discretion; our plan for completing the Science Goals does not require their input. We plan to also reach out to PIs of past HST programs from which we are gathering our data (e.g., Wes Fraser, Mike Brown, Keith Noll, Simon Porter, etc.) to see if they are interested in collaboration with no funding.

BYU recently began providing significant internal funding for new graduate students. We expect to receive such internal funding for 0.5 FTE of a TBD graduate student (“GS”) towards the proposed work at no cost to this proposal. Co-I Spencer, a current graduate student, is separately funded and the plan is that he will serve only as a consultant like the other Co-Is. He may contribute somewhat to the development of BINOPS that is here funded for the Graduate Student.

Thus, the nominal personnel resources are 0.075 FTE for PI Ragozzine (funded by this proposal) and 0.6 FTE GS (expected from a TBD Grad Student) with any other contributions as de minimis scientific consulting. We now describe the work required to complete the Science Goals in detail after which we will summarize the Science Goals.

Science Goal 1: Detection Probability

Solar system small bodies often have “moons” or “binary companions” which we’ll call “secondaries.” A single HST visit (all that is available for the majority of objects) can only discover such secondaries and cannot characterize their orbits. Therefore, the key characteristics of binaries accessible to this program are discovery properties of the secondary apparent from a small number (3-8) dithered images (usually WFPC2 or WFC3) taken in a single visit. These include the separation in RA and Dec and the brightness of the secondary (expressible both as absolute brightness and brightness relative to the primary). Approximately 500 HST visits over several programs have been devoted to the search for these secondaries (often later accompanied by full orbital characterization).

Secondaries that are too faint and/or too close to the primary cannot be reliably detected (e.g., SNR >~20). Because small bodies are point sources, the size/shape of the Point Spread Function (PSF) determines whether it is possible to distinguish between close primaries and secondaries. For example, a rough rule of thumb is that a secondary with a brightness ratio of x magnitudes can be detected if it is more than x pixels separated from the primary. There are three regimes: well-separated (“resolved”) binaries (where the two components are separated by >~2 PSF FWHM or >~5 pixels); blended (“semi-resolved”) binaries (where the two components are only readily visible if modeled jointly); and non-detections (which could be “unresolved” compact binaries).

In order to determine whether the frequency/properties of OSSBs are different for different populations, we must understand what secondaries could have been detected if they were present. This provides the characterization of the observational or selection bias, called “completeness”. It is expected that nearly all secondaries that are detectable are known in existing OSSB catalogs. Almost no work has been done on completeness, severely limiting the study of OSSBs. The exception is Porter et al. 2024 which provides a roadmap for this Science Goal.

We approach this problem probabilistically. The Detection Probability (DP) refers to the probability of detecting binary companions as a function of separation (s), brightness (b, related to SNR), and relative brightness (Δmag). Thus, the goal is to describe the DP function: DP(s, b, Δm). The gold standard for DP calculations is injection of thousands of simulated secondaries and blind recovery (Porter et al. 2024). With the limited funding, this is beyond the scope of this project. We will use heuristics from past experience and Porter et al. 2024 to characterize the functional form of the DP function, with a focus on the cameras used in the majority of the observations (WFPC2 and WFC3). We will consider only the first orbit of the first HST Visit of each object, removing the biasing effect of “follow-up observations.”

More than 90% of the HST data consist of 3-8 dithered images in visible filters sensitive to (unblended) objects down to about V ≈ 26. All objects have well-known pixel positions in the images. These will be used to perform a single PSF fit (likely using open-source PSF fitting software nPSF from Nelsen et al. 2025) on each image. These will then be co-registered, stacked, and median filtered after subtracting the PSF. The resulting difference image will be used to determine the DP function for this object. This will be repeated for >95% of the HST observed objects, about 500 minimum. Given the need to complete this goal in a short amount of time, a very conservative detection limit will be used to avoid false positives and false negatives; this should have only a mild effect on our major science conclusions.

For a statistical analysis at the ensemble-level, many potential issues lead to small systematic uncertainties that will not affect our conclusions. We will briefly investigate such issues as original target selection, poor PSF fits, primary-secondary motion, and lightcurves to minimize biases.

Science Goal 2: BINary Orbit Population Simulator (BINOPS)

Survey simulators that use forward models of populations are the most rigorous method for characterizing a biased population (e.g., the Origin Survey of the Outer Solar System Survey Simulator in Lawler et al. 2018 or the Planetary System Simulator for exoplanets in He et al. 2018,2019). Our next goal is to develop an OSSB focused BINary Orbit Population Simulator (BINOPS). This consists of a) a parametrization of the binary frequency used in a forward model to generate a synthetic true “physical” catalog, b) an observational “biasing” model that turns a physical catalog into a synthetic “observed” catalog using the DPs above, and c) a Bayesian likelihood calculator that determines the probability that the proposed catalog matches the actual HST observed OSSBs.

Forward Model. Binary frequency (F) will be described as a function of semi-major axis (or primary radius or Hill radius), eccentricity, inclination, primary size, and brightness ratio. This is typically done by parametrizing the differential distribution using a flexible but theoretically motivated function form. For example, the binary frequency as a function of semi-major axis is probably well-described by a power-law ∂F/∂a ∝ aβ or a broken power law (e.g., Porter & Grundy 2012). The parameters will divided by population (βCold TNOs, βHot TNOs, βTrojans, βCentaurs) each with their own normalization constant which is also inferred. (HST-observed objects will be classified into these categories based on Volk & Van Leurhoven 2025.) With this parametrization, each HST observed small body will be potentially populated with a binary companion (or not) with known orbital properties (averaging over orientation angles). Using standard methods and the observation properties of the HST data (e.g., distance to the small body), this catalog is cast into observational parameters (separation and brightness). Some of the scientific investigation of this project is to determine the best methods for parametrizing and implementing the forward model.

Biasing Model. The synthetic physical catalog of binaries can then be biased using the Detection Probabilities from Science Goal 1. This “convolution” can be done probabilistically (e.g., fractional detections are allowed). The result is a synthetic observed catalog.

Likelihood Model. There are multiple plausible methods for determining the probability that the actual HST catalog is a match for the synthetic observed catalog (the Bayesian “likelihood”). A starting point will be to use a grid of either observed parameters (separation-brightness) or physical parameters (semi-major axis, eccentricity, inclination, primary size, and brightness ratio) and determine the likelihood as a Poisson process with the rate given by the synthetic observed catalog and the detections given by the actual HST catalog. This method allows us to use repeat the synthetic catalog generation a very large number (probably hundreds) of times to reduce Monte Carlo noise, though the resulting likelihood will still be “stochastic.” This method is frequently used in exoplanet population synthesis (e.g., Neil & Rogers 2020) on somewhat simple populations. Part of the research will be to identify a likelihood model that answers scientific questions with a reasonable computational and personnel cost.

BINOPS will be validated by fitting synthetic populations to test the ability to accurately and precisely recover population parameters.

Science Goal 3: Addressing Scientific Questions

We will use Bayesian parameter inference methods (emcee, Foreman-Mackey et al. 2013) to apply BINOPS to the known HST population. While there will be many parameters (e.g., ~40, ~10 for each of 4 populations), this is similar in scale to analyses our group has succeeded at in the past. Individual likelihood evaluations will likely take ~seconds and our computational resources allow for about 109 likelihood evaluations which should be more than sufficient for successful parameter inference.

Nominally, the inferred parameters and the associated physical catalogs they represent are sufficient to address our science goals directly, without a customized analysis. For example, we will have posterior probability distributions for the frequency of binaries as a function of semi-major axis for the Trojan, Centaur, Cold TNO, and Hot TNO population, allowing us to directly answer the science question posed in Science Goal 3a, essentially in a single plot!

We may explore different parametrizations or methods to address specific questions. For example, Science Goal 3c can be addressed by using a mixture of two simple populations (“moon”-like and “binary”-like) with a cutoff in primary absolute magnitude.